## 1. EVA Task Data
Federated Learning for Edge Computing - Fraud Detection - Earned Value Analysis
Status Date: 30 November 2025
WBS ID | Task Name | Phase | Planned Value PV ($) | % Complete | Earned Value EV ($) | Actual Cost AC ($) | Status
1.1 | Project Initiation & Charter Development | Planning & Management | 1000 | 100 | 1000 | 1000 | Completed
1.2 | Stakeholder Analysis & Communication Plan | Planning & Management | 600 | 100 | 600 | 1200 | Completed
1.3 | Risk Management Planning | Planning & Management | 800 | 100 | 800 | 800 | Completed
1.4 | Agile-Scrum Framework Setup | Planning & Management | 400 | 100 | 400 | 400 | Completed
2.1 | Business Requirements Gathering | Requirements Analysis | 1000 | 100 | 1000 | 2000 | Completed
2.2 | Functional Requirements Documentation | Requirements Analysis | 1008 | 100 | 1008 | 1008 | Completed
2.3 | Non-Functional Requirements (Performance, Security) | Requirements Analysis | 864 | 100 | 864 | 864 | Completed
2.4 | Data Privacy & Compliance Analysis (GDPR, PCI-DSS) | Requirements Analysis | 800 | 70 | 560 | 560 | On Track
2.5 | Fraud Detection Use Case Analysis | Requirements Analysis | 960 | 70 | 672 | 672 | On Track
3.1 | Federated Learning Architecture Design | System & Architecture Design | 1600 | 70 | 1120 | 1120 | On Track
3.2 | Edge Node Architecture Design | System & Architecture Design | 1296 | 70 | 907.2 | 907.2 | On Track
3.3 | Central Aggregation Server Design | System & Architecture Design | 1152 | 30 | 345.6 | 345.6 | In Progress
3.4 | Communication Protocol Design (gRPC/REST) | System & Architecture Design | 864 | 30 | 259.2 | 259.2 | In Progress
3.5 | Database & Storage Architecture | System & Architecture Design | 720 | 30 | 216 | 216 | In Progress
3.6 | Security Architecture & Encryption Design | System & Architecture Design | 1232 | 30 | 369.6 | 369.6 | In Progress
9.1 | Sprint Planning & Management (Month 1) | Project Management | 800 | 100 | 800 | 800 | Completed
9.2 | Sprint Planning & Management (Month 2) | Project Management | 800 | 100 | 800 | 800 | Completed
TOTAL |  |  | 15896 |  | 11721.6 | 13321.6

## 2. EVA Summary
Earned Value Analysis Summary - 30 November 2025
Project: | Federated Learning for Edge Computing - Fraud Detection
Status Date: | 30 November 2025
Methodology: | Agile-Scrum
Budget at Completion (BAC): | $65,256.00
PRIMARY EVA METRICS
Metric | Formula | Value | Interpretation
Planned Value (PV / BCWS) | Sum of PV for tasks scheduled | 15896 | Total planned budget for work scheduled through status date
Earned Value (EV / BCWP) | Sum of (PV × % Complete) | 11721.6 | Value of work actually completed
Actual Cost (AC / ACWP) | Sum of actual expenditures | 13321.6 | Total actual costs incurred
VARIANCE ANALYSIS
Metric | Formula | Value | Interpretation
Schedule Variance (SV) | EV - PV | -4174.4 | BEHIND Schedule: Behind by $4,174.40
Cost Variance (CV) | EV - AC | -1600 | OVER Budget: Over budget by $1,600.00
PERFORMANCE INDICES
Metric | Formula | Value | Interpretation
Schedule Performance Index (SPI) | EV / PV | 0.73739 | Behind: Earning $0.74 for every $1.00 planned
Cost Performance Index (CPI) | EV / AC | 0.87989 | Over Budget: Earning $0.88 for every $1.00 spent
FORECASTING METRICS
Metric | Formula | Value | Interpretation
Estimate at Completion (EAC) | BAC / CPI | 74163.4529 | Projected total cost at project completion (Original: $65,256.00)
Estimate to Complete (ETC) | EAC - AC | 60841.8529 | Additional funds required to complete the project
Variance at Completion (VAC) | BAC - EAC | -8907.4529 | Expected overrun at completion
To-Complete Performance Index (TCPI-BAC) | (BAC - EV) / (BAC - AC) | 1.0308 | Performance efficiency needed: 1.03 to meet original budget

## 3. Management Summary
EARNED VALUE ANALYSIS - MANAGEMENT SUMMARY
EXECUTIVE SUMMARY
As of 30 November 2025, the Federated Learning for Edge Computing - Fraud Detection has completed 2 months of its 8-month lifecycle. KEY FINDINGS: 1. SCHEDULE PERFORMANCE: • Schedule Performance Index (SPI): 0.74 • Status: BEHIND schedule • Schedule Variance: $-4,174.40 • The project is currently not meeting planned progress 2. COST PERFORMANCE: • Cost Performance Index (CPI): 0.88 • Status: OVER budget • Cost Variance: $-1,600.00 • The project is experiencing cost overruns 3. BUDGET PROJECTION: • Original Budget (BAC): $65,256.00 • Projected Final Cost (EAC): $74,163.45 • Expected Variance: $-8,907.45 (overrun) • Remaining Budget Required (ETC): $60,841.85
RISK ASSESSMENT
Overall Project Risk Level: HIGH RISK IDENTIFIED CONCERNS: ⚠ Cost Overruns Detected: Two tasks experienced actual costs at 2× planned budget - Stakeholder Analysis: $600.00 over budget - Business Requirements: $1,000.00 over budget
MANAGEMENT RECOMMENDATIONS
IMMEDIATE ACTIONS REQUIRED: 1. COST CONTROL: ✓ Investigate root causes of cost overruns in planning phase ✓ Implement stricter change control procedures ✓ Review resource allocation for remaining phases ✓ Consider negotiating vendor contracts for upcoming procurement 2. SCHEDULE OPTIMIZATION: ✓ Leverage current schedule advantage to build buffer ✓ Identify opportunities to fast-track critical path activities ✓ Maintain current momentum in requirements and design phases 3. QUALITY ASSURANCE: ✓ Ensure quality is not compromised due to cost pressures ✓ Implement rigorous code review processes early ✓ Allocate sufficient time for testing phases 4. STAKEHOLDER COMMUNICATION: ✓ Present EVA findings in next steering committee meeting ✓ Discuss budget re-baseline options if CPI trend continues ✓ Set realistic expectations for project completion cost 5. RISK MITIGATION: ✓ Develop contingency plans for Model Development phase (highest risk) ✓ Establish reserve fund for unforeseen technical challenges ✓ Monitor CPI and SPI trends weekly
PROJECT HEALTH DASHBOARD
Schedule Health | At Risk
Cost Health | At Risk
Overall Progress | 18.0% Complete
Budget Consumed | 20.4%