## 1. Resource Sheet
Federated Learning for Edge Computing - Fraud Detection - Resource Budget
Resource Name | Role | Hourly Rate (USD) | Total Allocated Hours | Total Cost (USD)
Project Manager | Project Manager | 25 | 592 | 14800
Data Scientist 1 | Data 1 | 20 | 552 | 11040
Data Scientist 2 | Data 2 | 20 | 480 | 9600
Software Engineer 1 | Software 1 | 18 | 456 | 8208
Software Engineer 2 | Software 2 | 18 | 360 | 6480
QA Engineer | QA Engineer | 15 | 328 | 4920
DevOps Engineer | DevOps Engineer | 22 | 464 | 10208
TOTAL |  |  |  | 65256

## 2. Cost Sheet - Tasks
Federated Learning for Edge Computing - Fraud Detection - Task-Level Costs
WBS ID | Task Name | Project Phase | Assigned Resource | Planned Hours | Hourly Rate (USD) | Task Cost (USD)
1.1 | Project Initiation & Charter Development | Planning & Management | Project Manager | 40 | 25 | 1000
1.2 | Stakeholder Analysis & Communication Plan | Planning & Management | Project Manager | 24 | 25 | 600
1.3 | Risk Management Planning | Planning & Management | Project Manager | 32 | 25 | 800
1.4 | Agile-Scrum Framework Setup | Planning & Management | Project Manager | 16 | 25 | 400
2.1 | Business Requirements Gathering | Requirements Analysis | Project Manager | 40 | 25 | 1000
2.2 | Functional Requirements Documentation | Requirements Analysis | Software Engineer 1 | 56 | 18 | 1008
2.3 | Non-Functional Requirements (Performance, Security) | Requirements Analysis | Software Engineer 2 | 48 | 18 | 864
2.4 | Data Privacy & Compliance Analysis (GDPR, PCI-DSS) | Requirements Analysis | Data Scientist 1 | 40 | 20 | 800
2.5 | Fraud Detection Use Case Analysis | Requirements Analysis | Data Scientist 2 | 48 | 20 | 960
3.1 | Federated Learning Architecture Design | System & Architecture Design | Data Scientist 1 | 80 | 20 | 1600
3.2 | Edge Node Architecture Design | System & Architecture Design | Software Engineer 1 | 72 | 18 | 1296
3.3 | Central Aggregation Server Design | System & Architecture Design | Software Engineer 2 | 64 | 18 | 1152
3.4 | Communication Protocol Design (gRPC/REST) | System & Architecture Design | Software Engineer 1 | 48 | 18 | 864
3.5 | Database & Storage Architecture | System & Architecture Design | Software Engineer 2 | 40 | 18 | 720
3.6 | Security Architecture & Encryption Design | System & Architecture Design | DevOps Engineer | 56 | 22 | 1232
3.7 | Infrastructure & Deployment Architecture | System & Architecture Design | DevOps Engineer | 48 | 22 | 1056
4.1 | Credit Card Dataset Acquisition & Preparation | Data Preprocessing | Data Scientist 1 | 56 | 20 | 1120
4.2 | Data Cleaning & Missing Value Handling | Data Preprocessing | Data Scientist 2 | 64 | 20 | 1280
4.3 | Feature Engineering & Selection | Data Preprocessing | Data Scientist 1 | 72 | 20 | 1440
4.4 | Data Partitioning for Federated Nodes | Data Preprocessing | Data Scientist 2 | 56 | 20 | 1120
4.5 | Imbalanced Data Handling (SMOTE/ADASYN) | Data Preprocessing | Data Scientist 1 | 48 | 20 | 960
4.6 | Data Privacy Preservation (Differential Privacy) | Data Preprocessing | Data Scientist 2 | 40 | 20 | 800
5.1 | Base Model Selection & Configuration (MLP/XGBoost) | Model Development | Data Scientist 1 | 64 | 20 | 1280
5.2 | Local Model Training Implementation | Model Development | Data Scientist 1 | 80 | 20 | 1600
5.3 | Federated Averaging (FedAvg) Algorithm Implementation | Model Development | Data Scientist 2 | 88 | 20 | 1760
5.4 | Hierarchical Federated Learning Implementation | Model Development | Data Scientist 2 | 72 | 20 | 1440
5.5 | Model Aggregation Server Development | Model Development | Software Engineer 1 | 96 | 18 | 1728
5.6 | Edge Client Application Development | Model Development | Software Engineer 2 | 104 | 18 | 1872
6.1 | Edge Node Setup & Configuration | Edge Deployment | DevOps Engineer | 80 | 22 | 1760
6.2 | Containerization (Docker/Kubernetes) | Edge Deployment | DevOps Engineer | 72 | 22 | 1584
6.3 | CI/CD Pipeline Setup | Edge Deployment | DevOps Engineer | 64 | 22 | 1408
6.4 | Network Configuration & Load Balancing | Edge Deployment | DevOps Engineer | 48 | 22 | 1056
6.5 | Monitoring & Logging Setup (Prometheus/Grafana) | Edge Deployment | DevOps Engineer | 56 | 22 | 1232
6.6 | API Gateway & Service Mesh Implementation | Edge Deployment | Software Engineer 1 | 64 | 18 | 1152
6.7 | Database Integration & Optimization | Edge Deployment | Software Engineer 2 | 56 | 18 | 1008
7.1 | Unit Testing - Model Components | Testing & QA | QA Engineer | 72 | 15 | 1080
7.2 | Integration Testing - Federated System | Testing & QA | QA Engineer | 88 | 15 | 1320
7.3 | Performance Testing & Benchmarking | Testing & QA | QA Engineer | 64 | 15 | 960
7.4 | Security Testing & Penetration Testing | Testing & QA | QA Engineer | 56 | 15 | 840
7.5 | Privacy Validation & Compliance Testing | Testing & QA | Data Scientist 1 | 48 | 20 | 960
7.6 | Model Performance Evaluation (Accuracy, F1-Score) | Testing & QA | Data Scientist 2 | 56 | 20 | 1120
7.7 | User Acceptance Testing (UAT) | Testing & QA | Project Manager | 40 | 25 | 1000
7.8 | Bug Fixing & Issue Resolution | Testing & QA | Software Engineer 1 | 64 | 18 | 1152
7.9 | Regression Testing | Testing & QA | QA Engineer | 48 | 15 | 720
8.1 | Technical Documentation - Architecture | Documentation & Reporting | Software Engineer 1 | 56 | 18 | 1008
8.2 | API Documentation & Developer Guide | Documentation & Reporting | Software Engineer 2 | 48 | 18 | 864
8.3 | User Manual & Deployment Guide | Documentation & Reporting | DevOps Engineer | 40 | 22 | 880
8.4 | Model Documentation & Research Paper | Documentation & Reporting | Data Scientist 1 | 64 | 20 | 1280
8.5 | Experiment Results & Performance Analysis Report | Documentation & Reporting | Data Scientist 2 | 56 | 20 | 1120
8.6 | Project Final Report & Lessons Learned | Documentation & Reporting | Project Manager | 72 | 25 | 1800
8.7 | Presentation & Stakeholder Demo | Documentation & Reporting | Project Manager | 32 | 25 | 800
8.8 | Knowledge Transfer & Training | Documentation & Reporting | Project Manager | 40 | 25 | 1000
9.1 | Sprint Planning & Management (Month 1) | Project Management | Project Manager | 32 | 25 | 800
9.2 | Sprint Planning & Management (Month 2) | Project Management | Project Manager | 32 | 25 | 800
9.3 | Sprint Planning & Management (Month 3) | Project Management | Project Manager | 32 | 25 | 800
9.4 | Sprint Planning & Management (Month 4) | Project Management | Project Manager | 32 | 25 | 800
9.5 | Sprint Planning & Management (Month 5) | Project Management | Project Manager | 32 | 25 | 800
9.6 | Sprint Planning & Management (Month 6) | Project Management | Project Manager | 32 | 25 | 800
9.7 | Sprint Planning & Management (Month 7) | Project Management | Project Manager | 32 | 25 | 800
9.8 | Sprint Planning & Management (Month 8) | Project Management | Project Manager | 32 | 25 | 800
TOTAL | [5 empty] | 65256

## 3. Time-Phased Budget
Federated Learning for Edge Computing - Fraud Detection - Time-Phased Budget (8 Months)
Month | Planned Activities | Resource Cost (USD) | Cumulative Cost (USD)
October 2025 | • Project Management • Requirements Analysis • Planning & Management | 6472 | 6472
November 2025 | • Project Management • System & Architecture Design • Requirements Analysis | 6608 | 13080
December 2025 | • Project Management • System & Architecture Design • Data Preprocessing | 7072 | 20152
January 2026 | • Project Management • Model Development • Data Preprocessing | 6400 | 26552
February 2026 | • Project Management • Edge Deployment • Model Development | 10960 | 37512
March 2026 | • Project Management • Edge Deployment • Testing & QA | 9320 | 46832
April 2026 | • Project Management • Documentation & Reporting • Testing & QA | 10744 | 57576
May 2026 | • Project Management • Documentation & Reporting | 7680 | 65256
TOTAL |  | 65256

## 4. Budget Summary
Federated Learning for Edge Computing - Fraud Detection - Budget Summary
Project Title: | Federated Learning for Edge Computing - Fraud Detection
Duration: | 8 months (October 2025 - May 2026)
Methodology: | Agile-Scrum
Domain: | FinTech / AI / Edge Computing
BUDGET BREAKDOWN
Total Direct Resource Cost: | 65256
Calculation: | Sum of (Hours × Hourly Rate) for all tasks
Overhead Cost (30%): | 19576.8
Includes: | Infrastructure, Tools, Admin, Contingency
FINAL TOTAL PROJECT BUDGET: | 84832.8
Formula:
COST DISTRIBUTION BY PHASE
Data Preprocessing | 6720
Documentation & Reporting | 8752
Edge Deployment | 9200
Model Development | 9680
Planning & Management | 2800
Project Management | 6400
Requirements Analysis | 4632
System & Architecture Design | 7920
Testing & QA | 9152